Contents

sl. No.	Topic	     Page No.

1.	State Profile

1.1 Historical Background of the State

2.	Development of Elementary Education,

2.1 	Primary Education,

2.2 	Middle School

3.	Sarva Shiksha Abhiyan in Manipur: A Vision and Mission

3.1 	Aims  of SSA in Manipur,

3.2 	Objective of SSA in Manipur

3.3 	Component of SSA in Manipur

3.4 	Management Structure for programme

Implementation and Integration with Current Efforts

3.5 	Illustrative Management Structure at State,

District and Sub-districts Levels.

3.6 	Governing Council

3.7 	Executive Committee

3.8 	Meeting of the Governing Council and

Executive Committee

3.9	Training of State, District and Block Level

Educational Functionaries and NGO’s

3.10	Preparation of Annual Work Plan and Budget.

AWP&B 2005-06, for Implementation of SSA

4.	Basic Information/Data

5.	Progress in different interventions

6.	Financial Status of SSA in Manipur

1. State Profile

Manipur is one of the Border States in the northeastern part of the country having an international boundary of about 352 kms. long stretch of land with Myanmar in the east. It is bounded by Nagaland in the north, Assam in the west and Mizoram in the south. It has a total area of 22327 sq. kms. It lies between 23.80 N to 25.70N latitude and 93.50E to 94.80E longitude.

Geographically, the State of Manipur could be divided into two regions, viz. the hill and the valley. The valley lies in the central part of the State and the hills surround the valley. The average elevation of the valley is about 790 m above the sea level and that of the hills is between 1500 m and 1800m. The hill region comprises of five districts viz. Senapati, Tamenglong, Churachandpur, Chandel and Ukhrul and the valley region consists of four districts, viz. Imphal East, Imphal West, Thoubal and Bishnupur. The hill districts occupy about 90 percent (20089 sq km) of the total area of the State and the valley occupies only about tenth (2238 sq km) of the total area of the State. Imphal is the capital city of Manipur.

1.1	HISTORICAL BACKGROUND :

Manipur existed as a princely State in its early stage, involved in disputes with its neighbour Burma (Myanmar ).  At one point of time, Manipur  raided into the deep into the western frontier of  Burma. This resulted in the Burmese invasion of Manipur. Thereafter they conquered and ruled Manipur for 7 years (1819 - 1826).

During this period the then king Gambhir Singh of Manipur took shelter in Cachhar district of Assam. He re-organised the army there, and with the assistance of the British he ousted the Burmese. Slowly, the British started interfering in the administration of Manipur. This developed into a full fledged war with the British, where the Manipuri heroes faced the wellarmed (with guns) and massive British forces with swords and spears. The last phase of this battle was fought at Khongjom and ended on 23rd April 1891.

The Manipuri forces at Khongjom, led by Major Paona were defeated by the British forces. Many soldiers, including Major Paona himself, had laid down their lives in the battle field. So this day, 23rd April has been commemorated every year as “Khongjom Day “ and by delcaring a state holiday.

After the battle of Khongjom , the palace was captured and subsequently the Yuvraj of Manipur Tikendrajit along with General Thangal were executed at a public place, on 13th August 1891.This day is still remember and observed as “Patriots Day“. Since from 1891,.After the defeat in the war Manipur came under British rule.

Page - 1

Another significant event is that the first free Indian tricolour flag was hoisted on the Indian soil by the I.N.A. led by Netaji Subashchandra Bose in Manipur on 14th April, 1944. Again in the second world war, Manipur was in the scene of many fierce battles between the Japanese and Allied forces. Many soldiers and officers of the Allied forces lost their lives in these battles and their final resting places are still maintained in two cemeteries by the British War Graves Commission in Manipur.

In the year 1947 on August 15, Manipur regain her lost political status of a Sovereign independent Kingdom. The Maharaja of Manipur enacted the Manipur Constitution Act ,1947, establishing a democratic form of government with the Maharaja as the Executive Head and an elected legislative assembly.

Shortly after this, on 15th October 1949 Manipur was merged into India through a merger agreement between the Government of India and the then Maharaja of Manipur and ended the era of independent kindgom of Manipur. Hereafter, Manipur became a part of the union India.The State achieved its statehood in the year 1972.

2.  DEVELOPMENT OF ELEMENTARY EDUCATION IN MANIPUR

The ancient educational system of Manipur embodied the method of oral teaching and memorising the text by heart. The teaching and learning was effected through oral transmission of knowledge from generation to generation, before it was transcribed in the manuscripts.

Historically, until 1872, there was no primary school for formal education in Manipur. Efforts of Captain Gordon and Major General W.F. Nuthal, the political agents to open vernacular schools failed due to negative attitude of the people towards formal education which was exogenous to their cultural system and social structure. As a result, growth of primary education was very slow. In course of time, Maharaj Chandra Kirti gave his consent to Sir James Johnstone for establishing an English School in 1885 at Imphal. Later on the school was known as Johnstone Middle English School. During 1893-95, four Lower Primary Schools, three in Imphal and one in the hill area (at Mao) were opened. The enrolment at that time was confined to boys only as the parents were unwilling to send their daughters to these schools. Inspite of such prejudice against female education, a separate Girls’ Primary school was established in 1899 at Imphal. Only 12 girls came forward to join the school.

In order to cope with the expansion in all stages, the Department of Education was established in 1910. It is on record that the first batch of students appeared in Matric examination at Sylhet in 1909 as there were no high schools in Manipur in those days. In 1921 Johnstone M.E. School was upgraded to High School level and it was affiliated to Calcutta University. During 1931-41 many more High Schools came up as there was increasing demand of schools. In 1914, for the first time, Manipur produced a Doctor and in the subsequent years more and more students became  Engineers, Doctors and other Graduates.

Page - 2

During 1939 - 1943, education in Manipur was greatly effected because of the outbreak of World War II. It was only after 1944 that few schools started functioning in Manipur. In 1946, a college was established at Imphal in the name of Maharani Dhanamanjuri who donated a large sum of money i.e Rupees ten thousand for the cause of higher education.

After the World War-II there has been a sharp increase both in the number of schools and enrollment in Manipur. In the year 2005-06 the enrolment in class (I-V) was 3,62,999 in 2521 primary schools and that of class VI - VIII became 1,17,370 in 807 upper primary schools.

3.   SSA IN MANIPUR : A Vision and Mission

The Govt. of Manipur launched the centrally sponsored scheme of Sarva Shiksha Abhiyan (SSA) with a new vision as a mission mode in all the 9 districts of Manipur viz. Bishnupur, Chandel, Churachandpur, Imphal East, Imphal West, Senapati, Tamenglong, Thoubal and Ukhrul. Unlike in other States implementation of programme under SSA was started in Manipur in the year 2004-05 with the active participation of people at the grassroot level.

Sarva Shiksha Abhiyan (SSA) in Manipur is a multifaceted programme, which seeks to ensure the enrolment of all children in the age group of 6-14 in schools or alternative schools, retaining them and ensuring comparable elementary quality education. SSA is conceived as an essential national programme to achieve Universalization of Elementary Education (UEE) by 2010 by creating a sustainable and decentralized educational planning and management system, and invoking community participation in the whole process of the programme. This will be a major experiment of its kind where decentralization and community participation are being put together into practice on a large scale.

SSA has two aspects-

i)	It provides a wide convergent framework for implementation of elementary education schemes and

ii)	It is a programme with budget provision for the strengthening of vital areas to achieve  UEE.

3.1	Aims of SSA IN MANIPUR

The SSA launched in Manipur aims at providing useful and relevant elementary education for all children in the age-group 6-14 years as per the provisions of Article No. 45 of the Indian Constitution and 86th amendment of the Indian Constitution making Elementary Education a fundamental right. Another aim of SSA is to bridge social, regional and gender gaps with the active participation of the community in the management of schools with the purpose of providing useful and relevant education. Useful and relevant education means a quest for an education system that is not alienating and that draws on community solidarity. It aims at allowing children to learn about their natural environment and master them in a manner that allows the fullest harnessing of their human potential both spiritually and materially. This quest must also be a process of value based learning that allows children to work for each other’s well being rather than to permit mere selfish pursuits.

Page - 3

Sarva Siksha Abhiyan implemented in Manipur has realized the importance of Early Childhood Care and Education (ECCE) meant for children in the age-group 0-6 years and look at 0-14 years of age as a continuum. All efforts to support pre-school learning in ICDS centres or special pre-school centres in non ICDS areas had been made to supplement and complement the efforts being made by the Department of Women and Child Development, Govt. of Manipur to achieve the objectives of SSA.

3.2   Objectives of Sarva Siksha Abhiyan in Manipur.

SSA scheme for Universalisation of Elementary Education (UEE) in Manipur has been launched with specific objectives as is done in other States and UTs of India with a proper vision and mission as given below:-

1.	All children in Manipur should be in School, Education Guarantee Centre, Alternative school, back to school camp by 2005.

2.	All children in the state complete five years of primary schooling by 2007.

3.	All children complete eight years of schooling in Manipur by 2010.

4.	Focus should be made on elementary Education of satisfactory quality with emphasis on education for life in the state

5.	Bridge all gender and social category gaps at the primary stage by 2007 and at the elementary level by 2010 in the state, and

6.	Universal retention of children by 2010 in Manipur

3.3	COMPONENTS OF SSA

The components o.f SSA include appointment of teachers, teacher’s training, qualitative improvement of elementary education, provision of teaching learning materials, establishment of Block and Cluster Resources Centres (BRC, CRC) for academic support, construction of class rooms and school building, establishment of Education Guarantee Centres, integrated education of the disabled and distance education.

Page - 4

There are certain broad strategies central to SSA programme. They consist of institutional reforms, sustainable financing, community ownership, institutional capacity building, improving mainstream educational administration, habitation as unit of planning, accountability to community, priority to education of girls, focus on special groups, thrust on quality & role of the teachers, district elementary education plans, public private partnership etc.

3.4 	MANAGEMENT STRUCTURE FOR PROGRAMME IMPLEMENTATION AND INTEGRATION WITH CURRENT EFFORTS :

Article3.2 of chapter III of the Framework for implementation of SSA requires that there would be a State Mission Authority for UEE. Accordingly, an autonomous society, the “Sarva Shiksha Abhiyan State Mission Authority, Manipur” has been formed and  registered under the Manipur Societies Registration Act, 1987 (Manipur S.R. Act 1 of 1990) for implementation of SSA for UEE. The management structure of the society comprises of two bodies.

i)	The Governing Body at the apex for policy formulation with Chief Minister as ex-officio President.

ii)	The Executive Committee under the Chairmanship of the Chief Secretary to oversee the implementation of the programme.

The functions under the SSA project management will bear a fresh look and will gear up the jobs in a mission mode and team work. SSA functionaries will  comprise of the whole community through their active participation and will ensure the community empowerment and achievement.

With the intervention of SSA, the whole educational management will take a new shape. The existing system is working on certain areas which are mainly connected with routine works. The management system is also large and formal in nature. Now, SSA comes with certain additionality which can fill-up the gaps of performance and management of the existing system. So, interface between the formal and SSA management is essentially required for making SSA programme effective.

Page - 5

3.5 	ILLUSTRATIVE MANAGEMENT STRUCTURE AT STATE, DISTRICT AND SUB-DISTRICT LEVELS.

Article 3.3 of chapter III of the Framework for implementation of SSA allows  States to have their own management structures, respecting the diversity that exist in these structures across the states.

The State level office is headed by the Commissioner/Secretary in charge of school education and Director of Education (Schools) functions as ex-officio State Project Director (SPD) of SSA SMA. He is the member Secretary of the General body and the Executive Committee.

The District Project Office is headed by Zonal Education Officers (ZEO) functioning as District Project/Mission Coordinators with necessary supporting staff. The lowest functioning unit is at the cluster level i.e. the Cluster Coordinator or Cluster Resource Person (CRP). For the implementation of SSA programme, Implementation and Management Committees are set up at various levels and the lowest unit is the Village Education Committee (VEC).

4. Basic Information Data

The number of out of school children and the enrolment of school children are given in 7 different tables under the common heading “Basic Information Data”. These are the informations of 9 different districts of the state for 3 (three) consecutive year viz. 2003-04, 2004-05 and 2005-06.

The Tables 1 & 2 show the no. of out of school children of age group  (6-11) & (11-14) respectively of the different districts for the three consecutive years mentioned above.

The total no. of out of school children of the age group (6-14) is given in Table No. 3.

The tables 4, 5 and 6 shows the informations about the enrolment of children in school. The number of enrolment of school children belonging to primary grade and upper primary grade for the three consecutive years of the 9 different districts are shown in Table No. 4 and 5 respectively.

The total enrolment of school children belonging to primary grade and upper primary grade, i.e. the enrolment of Elementary section is shown in Table No. 6.

The total no. of school children of classes (I - V) and (VI - VIII) of the age group (6-14) is shown separately for each class in Table No. 7.

In the tables given in the consequence pages, the school children & the out of school children are categorised into SC (Schedule caste) & ST (Schedule tribe). Information regarding the no. of children belonging to SC / ST are shown in the tables in their respective categories.

Page - 7

The tables 1-7 give the status of the school children as well as out of school children of the State, Manipur for the 3 (three) consecutive years 2003-04, 2004-05 and 2005-06.

Page - 8

5.   Progress of different interventions

ANNUAL WORK PLAN & BUDGET (AWP&B) 2005-	2006 FOR IMPLEMENTATION OF SSA.

The Project Approval Board (PAB) had approved a budget of Rs. 5015.98 lakhs for implementation of SSA in the State during the year 2005-2006. The SSA State Mission Authority has utilised a sum of Rs. 2045.93 lakhs during the year 2005-06. Out of the total expenditure of Rs. 2045.93 lakhs, the Central share was Rs. 1327.44 lakh and the State share was Rs. 649 lakh for the year 2005-06. A balance of Rs. 69.49 lakh was spill over from the year 2004-05.

1.	Community Mobilisation & MEDIA :

Community Mobilisation for participation in SSA programme implementation is an important  intervention, since it is an effort to universalise elementary education by community ownership of the School System. It aims to provide useful, relevant and quality basic education to all children in the age group of 6-14 years by improving human capabilities through provision of Community - owned quality education in a mission mode. In order to participate community in the educational planning and implementation in the grass root level, creation of decentralised management system from State to District and District to Sub-District and capacity building are the main activities of the programme implementation.

Media plays a great role in generating public awareness for education in all sections of the society. Successful implementation of any programme requires public participation through awareness and motivation. With the objectives (keeping) in mind, Sarva Siksha Abhiyan, State Mission Authority Manipur has taken a multimedia campaign to make the public aware, motivated and leading finally to the participation towards universalisation of elementary education which is the main objective of the Sarva Shiksha Abhiyan

So far, various Trainings/Orientations/Workshops/Meetings have been taken up as a part of building capacity of SSA Key Functionaries of the state and district  as well as of community awareness programme throughout the state. Block level sports and literacy competitions have been taken for effective mobilisation of community that opens up the school as a social institution  to the community.

Page - 16

Training/orientation/workshop undertaken:

1st phase training programme on Capacity Building of VEC/BRP/CRP was conducted from 6-9 December, 2005 at Khuman Lampak Sports Complex Imphal by National Institute of Administrative Research, Lal Bahadur Shastri National Academy of Administration, Mussoorie and SSA State Mission Authority Manipur.

2nd phase training programme on Capacity Building of VEC/BRP/CRP was conducted from 27-30 March, 2006 at Khuman Lampak Sports Complex Imphal by National Institute of Administrative Research, Lal Bahadur Shastri National Academy of Administration, Mussoorie and SSA State Mission Authority Manipur.

2.	PLANNING & MIS :

Management Information System (MIS) :

Management Information System is the support system of the SSA Programmes. Under this activity, School-wise and Village-wise information are collected through DISE (District Information System in Education) 2005-06 and Entry of data to the Computer was completed by District staffs at the State Office. Reports were generated and incorporated  in the preparation of AWP&B 2006-07. For further improvement of MIS, at the state as well as at the districts, Rs.68.67 lakhs has been provided.

Page - 17

PLANNING :

Meetings/ Workshops/ Trainings were held on planning process at the state level, district level and block level with the Education functionaries by the National/ State Resource Persons for the decentralized planning and implementation under SSA programme.

| Sl. No. | ## Training of the staff | Organized by | No. of days | No. of participants |
| --- | --- | --- | --- | --- |
| 1. | Programme on preparation of AWP&B2005-06 for District/ State Component Plan. 24-25 Feb.2005. | SPD /SSA SMAM & TSG | 2 days | 50 |
| 2. | Workshop on DISE data entry 7-8 March 2005. | SPD /SSA SMAM & TSG/NIEPA | 2days | 30 |
| 3. | Three day Workshop on Planning for improvement of Elementary Edn., Indian Institute of Entrepreneurships Lal Mati, Guwahati 27 to 29 Oct., 2005. | TSG | 3 days |  |
| 4. | 1st Phase Training programme on preparation of AWP&B 2005-06 for District/State Component Plan. 5 – 10 Dec., 2005. | NIAR Mussoorie | 5 days |  |
| 5. | Workshop on DISE data entry 2nd & 3rd March, 2006. | NIEPA & SPD/SSA/SMAM | 2 days |  |
| 6. | 2nd Phase Training programme on preparation of AWP&B 2005-06 for District/State Component Plan. 28-30 March, 2006. | NIAR Mussoorie | 3 days |  |

Pedagogy and Quality Improvement :

Activities under DEP-SSA :

Sl. 	Activity	Target group	Venue	Time

No.

1.	3-Day Workshop on	32 participants	Conference	16-18

Development of Self 	from State Project	Hall of SCERT	June, 2005

Learning Materials	Office, District Project

(SLMs) for Distance	Offices, SCERT, DIETs,

Education programme	and BRCs.

2.	3-Day Workshop on	10 participants including	Conference Hall	8-10 Sept.,

Finalisation of 12 Self	SLM writters and subject	of Dte. of Edn.	2005

Learning Materials	experts.	(S)

for Distance Education.

Page - 18

Teachers Training:

20 days in-service teacher training for 1411 Primary and Upper Primary Teachers had been conducted in the District level. Details of districtwise achievements are given at Annexure (enclosed).

Page - 19

School Management, Maintenance & Teacher Grant sanctioned for 2005-06 :

Rs. 121.05 lakhs as Maintenance grant for 2421 Schools, Rs.70.00 lakhs as  school Management grant for 3500 Schools and Rs.67.76 lakhs as Teachers grant for13543 Teachers in Primary and Upper Primary Schools have been distributed.

School Management, Maintenance & Teacher Grant sanctioned for 2005-06 :

Rs. 121.05 lakhs as Maintenance grant for 2421 Schools, Rs.70.00 lakhs as  school Management grant for 3500 Schools and Rs.67.76 lakhs as Teachers grant for13543 Teachers in Primary and Upper Primary Schools have been distributed.

### 4.        Civil Works Progress :

No technical cell (Engineering House) has been established under SSA both at the State and District levels. However the works of technical supervision monitoring etc. for civil work programmes under SSA programme are being done by the DRDA of the District concerned. The following tables indicate the total approved by the GOI & achievement of the State thereof.

Total Outlay sanctioned in 2005-06 	     Expenditure                    Percentage

(including spill over)	    (Rs. in lakhs)                   expenditure

2110.90	          978.14	46.34

# Sl.	Name of  Component 	Approved including	Achievement

spill over		       including spill over                                                                                                                                                                                         	                                    Phy                  Fin                      Phy                 Fin

1.	B.R.C.	17	102	17	102

2.	C.R.C.	85	170	31	62

3.	Buildingless PS	211	527.5	149	170.5

4.	Buildingless UPS	61	183	61	183

5.	Dilapidated PS	77	192.5	46	115

6.	Dilapidated UPS	16	46	0	0

7.	Addl. Class Room	292	436	0	0

8.	Toilets/Urinals	1136	227.7	587	117.9

Page - 21

9.	Water Facility	856	128.5	281	42.14

10.	Boundary Wall	64	32	0	0

11.	Separation Wall	315	15.75	22	1.1

12.   Electrification	199	9.95	0	0

13.	New PS	0	0	0	0

14.	New UPS	20	40	0	0

Total		2110.9		978.14

5. INNOVATIVE ACTIVITIES :

(a) Development of new methods and techniques has been encouraged to achieve Quantity and Quality aspects in elementary education under different activities like ECCE, Girls/SC/ST Education and Computer Education and Rs. 85.75 lakhs sanctioned for this purpose. Residential camps for girls were held at the district level. Pictorial charts were developed in the local dialect of deferent tribal communities as a programme of SC/ST education.

(b) ECCE :

Early Childhood Care and Education (ECCE) and pre school learning are the most important part in improving the environment and participation of Children in formal school. In this part of life, foundation are laid down for all round development of motor, sensory, cognitive, language, social and personalities of a child.

The State Project Office had identified some new centers at the districts for setting up of new ECCE (AWC) centers at the places where there are no such centers.

All the BRC including District Co-ordinators concerned had been given training facilities for pre-schooling education.

Page - 22

Need based training of AWC/pre-school teachers in all the Districts except Chandel District and Imphal East District have been given for improvement of ECCE.

As per norms of SSA, setting up of Balwadis Centres in uncovered areas are under progress. In some districts, like Senapati, Bishnupur, etc. such scheme is implemented in full swing.

In the meeting of all DPOs, it was discussed at length and resolved to take up necessary action for the following activities as per guidelines and norms of ECCE under SSA :

- Strengthening pre-school component in ICDS/ECCE centers by need based training of AWC at the district level.

- Setting up of Balwadi Centres in uncovered areas.

- Organising training programme of community leaders.

- Development of materials including TLM for ECCE related activities.

- Development of Database on pre-schooling.

Page - 23

6. Integrated Education for Disabled (IED):

1.	Medical Assessment Camp has been completed in all 9 districts.

2.	Identification of children with special needs (CWSN) have been completed in all 9 districts and so far 7411 children have been identified for the year 2006.

3.	60 – Primary/upper primary teachers have been given 3 – month Foundation Course of R.C.I. Another 20 teachers for the said training programme are underway.

Page - 11

4.	A 2-Day orientation programme has been organized for general school teachers at District level in order to orient teachers for effective dealing with disabled children.

5.	We have conducted district level one-day workshop in all 9 – Districts for Awareness and Sensitization campaign of IED to BRP/CRP/VEC/ Teachers.

6.	Aids and Appliances have been distributed to 551  children with special needs of 5 hill districts.  Further, distribution of aids and appliances to 498 identified children with special needs (CWSN) four valley districts is underway.

7.	Observation of  “World Disabled Day” on the 3rd December of every year at the State level is conducted.

Page - 24

7. 	Free Text Book :

Under SSA, there is a provision of providing free text books for the SC/ST and Girls Students reading in Classes I - VIII within an upper ceiling of Rs. 150/- (Rupees one hundred and fifty) only per child/student. So, SSA cannot provide all the text books with this small amount. In the year, 2005-06 as many as 2,71,770 SC/ST and Girls Students have been provided free text books under this scheme.

Text books for Classes I – VIII are printed / published only in Manipuri and English medium Some tribal organizations desire to publish text books in their tribal languages but the State Government has no such provision at present. Text books are distributed a bit late in the year 2005-06 due to law and order problem in the State.

8. 	RESEARCH EVALUATION MONITORING AND SUPERVISION (REMS) :

(a) Data collection on Household Survey as on 30th Sept. 2005.

To improve the quality and effectiveness of Educational Planning and Management by collecting various data at a time in the prescribed formats, maintenance of the following Database is absolutely necessary for MIS at State and District levels.

(a)	Child Database

(b)	School Database.

(c)	General Database: Village profile, School Mapping & other required Information.

Meeting :

On 5th August, 2005 a meeting of State Co-ordinators of REMS and MIS with District Co-ordinators of the same Intervention was held at DE(S) Office, Lamphelpat, Imphal in connection with the Household survey and DISE Data collection.

Questionnaire/ Household Survey Format :

The Format has some modifications from the model  format:1 collection of household information ( Module-9: Micro-Planning NIEPA-New Delhi) after a thorough discussion on the contents of the format and the requirements of  information in the context of the state.

Page - 25

Printing:

Printing of formats has been done at the districts. The number of copies was based on the electoral roll 2005/ the census report 2001 with 10% wastage .

Training :

Training- cum- workshop for the district functionaries was held on 22nd August, 2005 to give a final shape to the arrangement of the survey and thereafter the training of district functionaries was conducted by the District co-ordinators in collaboration with the state officials in the respective districts in the last week of August, 2005 and distribution of the Household Format was done on the day of the training.

The officers mentioned below were assigned the work of liaison for different districts for successful conduction of  Household Survey.

1. T. Binodini Devi  S.C. ( Plg/ MIS )       		Thoubal & Imphal East.

2. L Thoiba Singh S.C   ( EGS / AIE)               	Bishnupur

3. N. Jit Singh S.C   ( Com. Mob. )           		Chandel

4. T. Guno Singh S.C   ( IED )                         	Ukhrul

5. N. Subon Singh S.C ( Quality Improvement )  	Tamenlong

6. L. Ibomcha  Singh S.C (ECCE )                        Senapati

7. L. Sagor Singh A S.C  ( EGS/AIE )               	Churachandpur

8. Dr. T. Geetchandra Sharma S.C  (REMS )        Imphal West

A review meeting was also held on 14 Nov. 2005 in connection with the progress of the Survey. As per report from the Districts conduct of household survey for child-wise information was completed in the month of January to March, 2006.  The Executive committee of SSA SMA Manipur sanctioned  Rs.2,09,553 for 4,19,106 household survey at the rate of Re.0.05 per household. However, scrutiny, compilation etc. could not

be done due to lack of manpower.

9. EGS AND AIE:

EGS is implemented in Manipur in the Government sector through the Village Education Committee. EGS  schools were started in Manipur since 2004-05 only. 733 EGS schools have been opened till 2005-06 and 17883 children have been covered in E GS schools.

Page - 26

AIE is implemented in the State mainly in the NGO sector. 60 (Sixty) NGOs have been involved in the implementation of AIE programme. 40(Forty) Residential Bridge Course Centres have been covered. 1008 Non Residential Bridge Course (NRBC) Centres have been opened and 26030 children have been covered. Names of the NGO’s are given below.

| LIST OF VOLUNTARY AGENCIES RUNNING BRIDGE COURSE CENTRES UNDER SSA PROGRAMME IN MANIPUR |  |  |  |
| --- | --- | --- | --- |
| Sl. No | Name of Voluntary Agency | Address | Remarks. |
| 1 | Social Development Organisation | Moirang Thana Leikai |  |
| 2 | Rural Development Organisation | Bishnupur Awang Leikai |  |
| 3 | Kwata Educational Volunteers Union | Kwata Santhong |  |
| 4 | The Indegeneous Arts & Social Development Organisation | Toubul |  |
| 5 | Centre for Social Upliftment | Keinou |  |
| 6 | The Women Action in Rural Development | Thanga Lawai |  |
| 7 | Socio Economic & Mass Education Volunteers Association | Paona Bazar Imphal | Implemnting the project in various districts. |
| 8 | Integrated Village Organisation | Ishok |  |
| 9 | Tribal Area Development and Cultural Development Organisation | Nungourok |  |
| 10 | Nungphura Village Development Society | P.O. Sugnu |  |
| 11 | Reach - m: Rural Education and Action for Change, Manipur | Pallel |  |
| 12 | Manipur Association for Social Sciences | Keishampat Imphal | Implemnting the project in various districts. |
| 13 | Rural Aid Services | Churachandpur |  |
| 14 | The Self Employed Tribals and Backward Womens' Association | Churachandpur |  |
| 15 | K. Patlein Multi-Purpose Development Training Centre | Churachandpur |  |
| 16 | Kuki Kanglai Lompi | Churachandpur |  |
| 17 | Young Paite Association | Churachandpur |  |
| 18 | Moulvaiphei Rural Health Training Centre | Churachandpur | Page - 27 |
| 19 | Hiyangthang Mayai Leikai Embroidery Association, | Hiyangthag |  |
| 20 | Organisation for Action for Social Integrated Services | Uripok |  |
| 21 | Uripok Educated Self Service Association | Uripok |  |
| 22 | Western Women Development Association | Ngairangbam |  |
| 23 | Voluntary Service Centre | Mutum Phibou |  |
| 24 | Rural Educational Development Institute | Mayanglangjing |  |
| 25 | The Manipur Vocational Institute, | Mekola Bazar |  |
| 26 | Natural and Human Resourch Development | Langol |  |
| 27 | Enviroment Protection Rosource Centre | Patsoi |  |
| 28 | Southern Imphal Youth Welfare Organisation | Mongsangei Ningthemcha Karong | Not implementing the project |
| 29 | Society for Economic State Craft. | Khumbong |  |
| 30 | The Integrated Rural Development Society | Lilong |  |
| 31 | Rural Voluntary Organisation | Yairipok |  |
| 32 | Youth Development Association | Yairipok |  |
| 33 | Centre for Social Ecological Development | Kakwa |  |
| 34 | Child and Women Welfare Association | J.N. Hospital Road. |  |
| 35 | Primier Rural Paradise, | Soibam Leikai |  |
| 36 | Naharup Pangong Makhng Awang Leikai Women Association | Naharup |  |
| 37 | Rural Health Development Centre | Lamlong |  |
| 38 | Council for Youth Development and Co-operation | keibi |  |
| 39 | Friendship Centre | Khurai Kongpal |  |
| 40 | Keirou Wangkhem Women Welfare Association, | Sandrok |  |
| 41 | Institute of Social Organisation | Luwangshangbam |  |
| 42 | Society for Progressive Development | Salanthong |  |
| 43 | Socio Economic Welfare Society | Khurai Heigrumakhong |  |
| 44 | The Women and Child Welfare Association | Kangpokpi | Page - 28 |
| 45 | Zoungam Institute for Community Resources Development, | Saikul |  |
| 46 | Kishan Development Association | Saikul |  |
| 47 | Paomei Development Society | Senapati |  |
| 48 | Integrated Rural Development Welfare Association | Senapati |  |
| 49 | Islamic Education Development Organisation | Sangaiyumpham |  |
| 50 | Wangjing Women and Girls Society, | Wangjing |  |
| 51 | Rural Development Society | Wangjing |  |
| 52 | The Loyalam Foundation | Yairipok |  |
| 53 | Human Institue of Life Line Services | Thoubal Ahokpam |  |
| 54 | The Ecological Useful Productive and Social Development Organisation | Thoubal Athokpam |  |
| 55 | Public English School | Thoubal |  |
| 56 | Integrated Rural Welfare Association | Yairipok |  |
| 57 | New Cannon Youth Cultural Club | Yaingangpokpi |  |
| 58 | Volunteers for Village Development | Ukhrul District |  |
| 59 | PASDO | Ukhrul District |  |
| 60 | Raphei Area Self Help Initiative Development Organisation | Ukhrul District |  |

Page -

Page - 17

Page - 29